## Submission plan updated
Hours per week
20 hours per week ~ 2 days
20 hours per week ~ 2 days
600 hours total
Key checkpoints
End date
Task (level 1) | Task breakdown (level 2) | Progress
context | Understand the context and requirements of image detection modelling within colloidal chemistry. | Done
context | Research choose and understand potential deep learning algorithm(s) suitable for the particle detection task. | Done
context | Write project plan (literature review, risk assessment, and project plan) | Done
Done
context | learning Tensorflow vs. Pytorch, CNN modelling practicalities | Done
setup | Generation of synthetic data. | Done
setup | Get a YOLO model traiing and predicting on synthetic data | Done
step 1: characterisation | Create synthetic data covering correct ranges of the variables to test | Progress
step 1: characterisation | Train a few models on varying data types/HPs | Progress
step 1: characterisation | Evaluate effectiveness of model on various synthetic data | Progress
step 2: time / accuracy trade off
step 2: holographic
| Evaluation of model on synthetic data. | 30
| Setup, train and compare new model versus previous algorithm(s) tested in the literature (e.g. YOLOv2-tiny). | 10-60
| Extension of training to evaluate role of disk area density in the image and particle overlap on the models’ performance. | 20
| Setup resources required for deployment of model to lab. | 10
| If model meets criteria of accuracy, speed, and robustness required then productsionisation and deployment to lab. | 90
| Evaluation of model on real experimental image data. | 30
| If necessary, retrain/fix model and redeploy to lab. | 0-60
| Generation of stacked-training data using accurate imaging theory of randomly-positioned spheres of radius R. | 20
| Training and evaluating of DL model to predict (x,y,z,r) from image stack. | 60 - 80 (Rough model creation planned for, refined model can be done if time)
| Role of particle number density ($\rho$) and particle overlap in accuracy/robustness of predictions. | 20
80

## Step 1 Characterisation details
| Data | Standard setup |  | Range to test | Training experiments: | Parameters constant |  |  | Parameters to set |  |  |  | Impurity parameters to set
| Image size | 416 |  |  |  | Image_h_w | luminosity range | min distance between | Density | Size | Size std | SNR | Impurity type | Impurities_density | Impurities_size | Impurities_size_std
| Diameter | 8.32 | +/- 0.1 to 0.5 |  | 1. Standard | 620 | 80-100% | 1 particle | 2% | 12 | 2 | 10 | None | - | - | -
| Density by area | 10% |  | test 1 to 20 | 2. density: 10 % | 620 | 80-100% | 1 particle | 10% | 12 | 2 | 10 | None | - | - | -
| Particle proximity | 8.32 |  |  | 3. Big particle std | 620 | 80-100% | 1 particle | 2% | 12 | 5 | 10 | None | - | - | -
| Impurities | None |  |  | 4.1 Low SNR | 620 | 80-100% | 1 particle | 2% | 12 | 2 | 5 | None | - | - | -
[5 empty] | 4.2 High SNR | 620 | 80-100% | 1 particle | 2% | 12 | 2 | 20 | None | - | - | -
[5 empty] | 5.1 Including impurities (circular) different in size | 620 | 80-100% | 1 particle | 2% | 12 | 2 | 10 | Circle | 1% | 4 | 1
[5 empty] | 5.2 Including impurities (circular) close in size | 620 | 80-100% | 1 particle | 2% | 12 | 2 | 10 | Circle | 1% | 7 | 1
[5 empty] | 5.3 Including impurities (square) same in size | 620 | 80-100% | 1 particle | 2% | 12 | 2 | 10 | Square | 0.5% | 12 | 5
Impurity parameters to set
| Comments: |  |  |  | Models to build | Image_h_w | luminosity_range | min distance between | Density | Size | Size std | SNR range | Impurity type | Impurities_density | Impurities_size | Impurities_size_std
| Assume that particle "situated" within 2 std of the centre. |  |  |  | 1. Standard | 620 | 80-100% | 1 particle | 1-12% | 12 | 2 | 4-25 | None | - | - | -
| When say 1 particle away min dist, mean 4 std. of radii euc distance between two centroids. |  |  |  | 3. Big particle std | 620 | 80-100% | 1 particle | 1-12% | 12 | 4 | 4-25 | None | - | - | -
[5 empty] | 5.1 Including impurities (circular) different in size | 620 | 80-100% | 1 particle | 1-12% | 12 | 2 | 4-25 | Circle | 0.5 to 1.2% | 5 | 3 | Square | 0.5% | 12 | 5
HPs to test
Setup
1 | train baseline | 200 epochs | batch 32
2 | tune test new HPs | 200 epochs | batch 32
3 | change freeze | 200 epochs | batch 32
4 | evaluate find best selection
Test diff data
1,2,3 | train 3 models on the 3 datasets (using above selected params and hps) | 200 epochs | batch 32
4 | evaluate on each test set
Test speed diff models
1,2,3 | for standard dataset test nano,small,medium
4 | for standard dataset test yolov8 nano,small?
5 | evluate time to predict and accuracy

## Yolo repos
Getting a yolo model working
Repo 1 (franzl): | Unknown env, could not get working (trial and error env was slow)
Repo 2 (amateur v3 repo) | Well documented, working but results were not logical - did not spend time to bug fix)
Repo 3 (darknet) | Standard repo, but built in c+ so can not annotate or understand the underlying code as well, which is essntial for this masters)
Repo 4 (ultralytics) | Well documented, in python pytorch, so was the one chosen - ability to upgrade to v8 if want)
Ultralytics (yolov5)
Training process
Within training there are some prepocessing steps:
flipping/blockout etc
HP tuning:
Mteric is weighted comb. Of precision, recaal, (10% at conf at 0.5 and 90% at 0.5-0.95
Genetic algorithm for HP selection:
Run for e.g. min 300 gens
mutation is used, with an 80% probability and a 0.04 variance to create new offspring based on a combination of the best parents from all previous generations
100s of gpu hours
Note that if overfitting, then increase augmentation hyperparameters
Freeze:
Gives similar results if just freeze backbone. Cut time to 75%
Baseline: | Train baseline using defaults (epochs = 300 but may do less if best is way before that)
Then adjust (HP/freezing/pretrained weights/number and processing of training images)
Notes on image creation | cCreate background images
1500 images per class
10000 instanes per class
1 hour: 4000, 1 epoch

## Evaluation
RMSE (in pixels): | Distance between true and predicted centre point
% particles detected with dist mismatch within a threshold
% particles detected
TP /FP/FN rate

## Submission plan
Term dates: | Length | Hours per week
1. ~6th June - 19th September | 15 weeks | 20 hours per week ~ 2 days
2. ~5th June - 18th September | 15 weeks | 20 hours per week ~ 2 days
600 hours total
Plan will be organised into 10 3-week "blocks" - equivalent of 6 days (60 hours) work each
|  | Key checkpoints |  | Finalise Project outline with supervisor |  | Projct Plan submission |  | End of first term: Have started deployment to lab (so integration to lab setup issues that take time to resolve are known) |  |  |  |  | Must have as a minimum: deployed 2D model, or a trained and evaluated 2D and 3D model. | Final submission (exact date tbc)
|  | End date |  | 2022-06-26 | 2022-07-17 | 2022-08-07 | 2022-08-28 | 2022-09-18 | 9 month gap | 2023-06-26 | 2023-07-17 | 2023-08-07 | 2023-08-28 | 2023-09-18
Task | Task breakdown (level 1) | Task breakdown (level 2) | Time for each task (hrs) | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10
Literature review
| Reading | Understand the context and requirements of image detection modelling within colloidal chemistry. | 30 | x
|  | Research choose and understand potential deep learning algorithm(s) suitable for the particle detection task. | 30 | x
| Writing | Write project plan (literature review, risk assessment, and project plan) | 20 |  | x
Particle tracking in two-dimensions
| Research, understand and experiment possible method practicalities. | Tensorflow vs. Pytorch, model implementation and retuning. | 10 |  | x
| Low-density systems | Generation of synthetic data. | 30 |  | x
|  | Training of model to predict (x,y,r (particle radius)). | 120 |  |  | x | x
|  | Evaluation of model on synthetic data. | 30 |  |  |  |  | x
|  | Setup, train and compare new model versus previous algorithm(s) tested in the literature (e.g. YOLOv2-tiny). | 10-60 |  |  |  |  | (Can be descoped to compare to literature only)
| High-density systems | Extension of training to evaluate role of disk area density in the image and particle overlap on the models’ performance. | 20
| Deployment | Setup resources required for deployment of model to lab. | 10 |  |  |  |  | Must have been started by here.
|  | If model meets criteria of accuracy, speed, and robustness required then productsionisation and deployment to lab. | 90 |  |  |  |  | Must have been started by here.
|  | Evaluation of model on real experimental image data. | 30
|  | If necessary, retrain/fix model and redeploy to lab. | 0-60 | [8 empty] | (May not be required) | (May not be required)
Particle tracking in three-dimensions
|  | Generation of stacked-training data using accurate imaging theory of randomly-positioned spheres of radius R. | 20
|  | Training and evaluating of DL model to predict (x,y,z,r) from image stack. | 60 - 80 (Rough model creation planned for, refined model can be done if time)
|  | Role of particle number density ($\rho$) and particle overlap in accuracy/robustness of predictions. | 20 | [9 empty] | (If time)
Report write up |  |  | 80 |  | Intro and background |  |  | Write up term 1 work here

## Sheet1
Level of a DS prof. not chemistry prof.
Thesis writing style: Objectives (separate to intro). What going to do. What you did and why. Conclusions, learnings and what future work.
Holidays
Meeting routine (every other week?) - Paul?
Deadline for submitting to you for review? | 2-1 weeks prior
Appreciate falicitating communication with PB and any practical implementation hurdles - if some hurdles are insummountable (PB doesn’t have the time/remote work incompatible then need to rescope).
How much can I use PB - relationship?
Holidays:
3-6 july
17-21 july
7-12 aug

## Risk assessment
Risk | Likelihood | Stage of discovery | Effects/impact on project | Mitigation steps taken
Model does not meet criteria due to algorithm shortfalls | Low | Identified within training of model step. | Would need to redo work with different algorithm. IMPACT: 20-90 hours | Do appropriate research into algorithms - both theory, and past use case usage
Shortfalls in model training/synthetic data work discovered when testing on experimental data. (E.g. synthetic data used was inappropriate) | Medium | Identified at model deployment stage. | Would need to adjust/redo model training and redeploy. IMPACT: 30-60 hours | Due to non-negligible risk, ensure sufficient time in plan after this step to redo if required. (As without this, key deliverable of project is missing).
System integration issues when deploying model. (E.g. latency in labview system when calling model - (data processing/writing to disk times), or deployment requires coming into bristol but remote working complicates this) | Medium (less known) | Identified at model deployment stage. | Would need to either: redo productionisation of model. IMPACT: 30 hours; Fix system integration issues. IMPACT: 30 hours. Remove deploment to lab from scope of project. | Ensure work on deployment has been initialised by end of term 1, so that any time consuming fixes or changes to the system that need to be done by other parties can be addressed in break. If deployment scoped out there are additional tasks outside of current plan time that can be done. | 47.8469
Access to computing resources | Low | Training model | Blocker (other work could be done in mean time). IMPACT: 0-30 hours | Scope out likely required resources and let relevant parties know as many details as possible when known. (E.g. dates/time/resource requried)
Unforseen issues. | Low | Throughout | Impact: Key deliverable(s) required for report not created. | Planned for a main deliverable of project to be completed by end of block 7, giving 2 blocks leeway in case of unforeseen hinderances.
Unforseen successes. | Low | Throughout | Run out of tasks for project - project scope too small. | Plan includes additional tasks that can be done if time.